# HealthConnect Clinic - Week 5 Project Summary

Data Analytics Track

AnalystLab Africa Experience Lab

Week 5: HealthConnect Solution Development & Implementation

Planned: complete data preparation checks, exploratory analysis, calculate 3-5 KPIs, build an initial dashboard, and produce written business insights.

Completed: all of the above. Data quality was confirmed clean with only explainable missing values; EDA was carried out across appointment, patient, history, reminder, waiting time, distance, and cancellation dimensions; five KPIs were defined, calculated, and interpreted; a Power BI dashboard was built and iteratively refined (chronological trend sorting, correct table references, consistent formatting, visual highlighting of top risk factors); six business insights were documented.

Key findings: distance to clinic and prior no-show history are the strongest attendance predictors found; reminders show a real but moderate effect; waiting time shows no meaningful relationship to no-shows; cancellations are a minor issue relative to no-shows.

Major challenges: early dashboard iterations required troubleshooting - incorrect table name references in DAX measures, chronological sort order on the date axis (resolved with a numeric YearMonthSort key), a circular sort dependency that had to be traced and cleared, and a measure being mistakenly used where a calculated column was needed for axis categories.

Important decisions: cancellations were explicitly excluded from the no-show rate denominator, since a cancelled appointment is a materially different patient action from a silent no-show; this decision is documented in the main report and can be revisited if HealthConnect's business needs require an all-bookings-inclusive rate instead.

Changes to Week 4 approach: no material changes; the KPIs proposed in Week 4 were confirmed as calculable and relevant, with cancellation rate added explicitly as a fifth KPI to ensure both outcome types were represented.

Cross-track collaboration completed: shared distance and prior no-show findings with the Data Science track as candidate predictive features for a future no-show prediction model.

Remaining work: the dashboard has been completed with all planned charts, accent highlighting, and a callout panel; remaining work is limited to final proofreading and packaging supporting files for submission.

Proposed Week 6 focus: refine the dashboard into a fully presentation-ready state if further design iteration is requested; deepen analysis of interaction effects (e.g. distance combined with reminder status); and formalize recommendations into a short set of operational actions for HealthConnect Clinic.